## Construction Schedule
CONSTRUCTION SCHEDULE — 5,000 SF Midtown Office Fitout
Project Start: May 04, 2026 ¦ Duration: ~22 Weeks ¦ Budget: $1,500,000
# | Activity | Duration (Days) | Start Date | End Date | Notes | Wk 1 05/04 | Wk 2 05/11 | Wk 3 05/18 | Wk 4 05/25 | Wk 5 06/01 | Wk 6 06/08 | Wk 7 06/15 | Wk 8 06/22 | Wk 9 06/29 | Wk 10 07/06 | Wk 11 07/13 | Wk 12 07/20 | Wk 13 07/27 | Wk 14 08/03 | Wk 15 08/10 | Wk 16 08/17 | Wk 17 08/24 | Wk 18 08/31 | Wk 19 09/07 | Wk 20 09/14 | Wk 21 09/21 | Wk 22 09/28 | Wk 23 10/05 | Wk 24 10/12 | Wk 25 10/19
PRECONSTRUCTION
1 | Landlord Plan Approval | 10 | 05/04/2026 | 05/13/2026
2 | DOB Permit Filing & Approval | 15 | 05/11/2026 | 05/25/2026 | Expediter engaged
3 | Subcontractor Buyout | 10 | 05/04/2026 | 05/13/2026
4 | Submittals & Shop Drawings | 15 | 05/18/2026 | 06/01/2026 | All trades
5 | Pre-Construction Meeting | 1 | 06/01/2026 | 06/01/2026 | Kick-off
DEMOLITION & ABATEMENT
6 | ACM Survey & Lead Testing | 3 | 06/08/2026 | 06/10/2026 | Environmental consultant
7 | Asbestos Abatement | 5 | 06/11/2026 | 06/15/2026 | Licensed abatement contractor
8 | Selective Demolition | 8 | 06/15/2026 | 06/22/2026 | Partitions, ceiling, MEP
9 | Slab Prep & Patching | 3 | 06/25/2026 | 06/27/2026 | After demo complete
ROUGH-IN (MEP)
10 | Plumbing Rough-In | 10 | 06/29/2026 | 07/08/2026 | Underground + risers
11 | HVAC Ductwork Rough-In | 15 | 06/29/2026 | 07/13/2026 | Main trunk + branches
12 | Electrical Rough-In | 12 | 07/02/2026 | 07/13/2026 | Panel, conduit, boxes
13 | Fire Sprinkler Rough-In | 8 | 07/06/2026 | 07/13/2026 | Mains + branch lines
14 | Fire Alarm Rough-In | 5 | 07/13/2026 | 07/17/2026 | Conduit + wire pull
15 | Low Voltage Rough-In | 8 | 07/13/2026 | 07/20/2026 | Cat6A + fiber
FRAMING & DRYWALL
16 | Metal Stud Framing | 10 | 07/13/2026 | 07/22/2026 | After MEP rough layout
17 | In-Wall MEP Coordination | 3 | 07/23/2026 | 07/25/2026 | All trades walk-through
18 | Insulation | 3 | 07/27/2026 | 07/29/2026 | Acoustic + fire rated
19 | Drywall Hang | 8 | 07/30/2026 | 08/06/2026 | Board + tape
20 | Drywall Finish (Tape & Spackle) | 8 | 08/06/2026 | 08/13/2026 | Level 4/5
CEILING
21 | ACT Grid Installation | 5 | 08/13/2026 | 08/17/2026 | Open office areas
22 | Drywall Ceiling Framing & Finish | 8 | 08/10/2026 | 08/17/2026 | Conference + reception
23 | Cloud Panel Installation | 3 | 08/20/2026 | 08/22/2026 | Lounge/collab areas
FINISHES
24 | Painting (Primer + 2 Coats) | 8 | 08/17/2026 | 08/24/2026 | All surfaces
25 | Floor Prep & Self-Leveling | 3 | 08/24/2026 | 08/26/2026 | Moisture test first
26 | Tile Installation (Pantry/Restrooms) | 5 | 08/27/2026 | 08/31/2026 | Porcelain + waterproofing
27 | LVT Installation | 5 | 08/31/2026 | 09/04/2026 | Open office
28 | Carpet Tile Installation | 4 | 09/03/2026 | 09/06/2026 | Offices + conference
29 | Base Installation | 3 | 09/07/2026 | 09/09/2026 | Rubber/wood base
MEP TRIM & CLOSE-IN
30 | HVAC Diffusers & Grilles | 4 | 08/31/2026 | 09/03/2026 | After ceiling
31 | DDC/BMS Controls & Programming | 5 | 09/03/2026 | 09/07/2026 | Zone controllers
32 | Electrical Devices & Fixtures | 5 | 08/31/2026 | 09/04/2026 | Outlets, switches, lights
33 | Plumbing Fixtures & Trim | 4 | 09/03/2026 | 09/06/2026 | Sinks, faucets, WC
34 | Sprinkler Head Trim | 2 | 09/03/2026 | 09/04/2026 | Concealed + pendant
35 | Fire Alarm Devices | 3 | 09/03/2026 | 09/05/2026 | Detectors, H/S, pulls
36 | Low Voltage Terminations | 5 | 09/07/2026 | 09/11/2026 | Patch, test, label
MILLWORK & SPECIALTIES
37 | Reception Desk Install | 3 | 09/07/2026 | 09/09/2026
38 | Pantry Cabinetry & Countertops | 5 | 09/07/2026 | 09/11/2026
39 | Glass Partitions & Doors | 5 | 09/03/2026 | 09/07/2026 | Conference rooms
40 | Signage & Wayfinding | 2 | 09/14/2026 | 09/15/2026 | ADA compliant
41 | Window Treatments | 3 | 09/14/2026 | 09/16/2026 | Motorized shades
42 | Toilet Partitions & Accessories | 3 | 09/10/2026 | 09/12/2026
FF&E & CLOSEOUT
43 | Furniture Delivery & Installation | 5 | 09/17/2026 | 09/21/2026 | Workstations, chairs, tables
44 | AV Installation & Programming | 4 | 09/17/2026 | 09/20/2026 | Displays, cameras, sound
45 | Access Control & CCTV | 3 | 09/17/2026 | 09/19/2026 | Card readers, cameras
46 | Punch List Walk-Through | 3 | 09/24/2026 | 09/26/2026 | A/E + Owner
47 | Punch List Completion | 5 | 09/28/2026 | 10/02/2026 | All trades
48 | TAB (Test & Balance) | 3 | 09/24/2026 | 09/26/2026 | AABC certified
49 | Commissioning | 3 | 09/28/2026 | 09/30/2026 | All systems
50 | FDNY / DOB Inspections | 3 | 10/01/2026 | 10/03/2026 | Final sign-offs
51 | Final Clean | 2 | 10/05/2026 | 10/06/2026
52 | Substantial Completion | 1 | 10/08/2026 | 10/08/2026 | TCO / Letter of Completion
53 | Move-In | 3 | 10/12/2026 | 10/14/2026 | Tenant occupancy
LEGEND:
PRECONSTRUCTION
DEMOLITION & ABATEMENT
ROUGH-IN (MEP)
FRAMING & DRYWALL
CEILING
FINISHES
MEP TRIM & CLOSE-IN
MILLWORK & SPECIALTIES
FF&E & CLOSEOUT

## Milestones
# | Milestone | Target Date | Status
1 | Landlord Approval Received | 05/18/2026 | Pending
2 | DOB Permits Issued | 06/01/2026 | Pending
3 | Demolition Complete | 06/29/2026 | Pending
4 | MEP Rough-In Complete | 07/27/2026 | Pending
5 | Framing & Drywall Complete | 08/17/2026 | Pending
6 | Ceiling Complete | 08/24/2026 | Pending
7 | Finishes Complete | 09/14/2026 | Pending
8 | MEP Trim Complete | 09/14/2026 | Pending
9 | Punch List Walk-Through | 09/28/2026 | Pending
10 | TAB & Commissioning Complete | 10/05/2026 | Pending
11 | DOB / FDNY Final Inspections | 10/05/2026 | Pending
12 | Substantial Completion / TCO | 10/12/2026 | Pending
13 | Tenant Move-In | 10/12/2026 | Pending