SCOPE OF WORK

Contech Office Fit-Out

| Project: | Contech Office Fit-Out |
| --- | --- |
| Duration: | March 30 – October 13, 2026 (~28 weeks) |
| Activities: | 23 (Linear Critical Path) |
| Source: | Primavera P6 XER Export |
| Date: | March 28, 2026 |

1. MOBILIZATION & DEMOLITION

- Site mobilization: temporary protection of building common areas, freight elevator pads, corridor protection per building rules

- Establish site logistics plan, dumpster and material staging

- Daily OSHA-compliant safety program and site housekeeping

- Selective demolition of existing partitions, ceiling grid, flooring, and MEP systems to slab

- Disconnect and cap all existing MEP services at points of origin

- Debris removal via building-approved hauling contractor

- ACM/lead survey and abatement if required (scope subject to survey results)

2. LAYOUT, FRAMING & METAL STUD PARTITIONING

- Laser layout of all partition locations per architectural drawings

- Install floor and ceiling track for metal stud partitions

- Metal stud framing: 3-5/8" and 2-1/2" steel studs at 16" o.c. per partition schedule

- Full-height slab-to-deck partitions at rated and acoustic locations

- Blocking and backing for millwork, TV mounts, grab bars, and heavy accessories

- Coordinate all in-wall MEP rough-in locations prior to board close

3. FIRST FIX MEP (ABOVE CEILING & IN-WALL)

- HVAC: ductwork distribution, fan coil connections, refrigerant piping, condensate drains

- Electrical: panel installation, branch circuit conduit and wiring, outlet and switch boxes

- Plumbing: domestic water and sanitary waste rough-in for pantry and restrooms

- Fire alarm: conduit and wire pull for smoke detectors, horn/strobes, pull stations

- Low voltage: Cat6A data cabling rough-in, pathway for fiber from building demarc

- Fire sprinkler pipe modification: relocate and add heads per new reflected ceiling plan

- Hydraulic calculations and DOB sprinkler permit

- All above-ceiling and in-wall work completed before drywall close and ceiling installation

4. DRYWALL CLOSING & CEILING INSTALLATION

- Single-side drywall closing after MEP inspection and sign-off

- 5/8" Type X gypsum board on rated partitions (1-hour rating where required)

- Insulation in all rated and acoustic partitions (R-13 minimum)

- Ceiling grid and hanger installation: ACT (2x2 or 2x4) in open office areas

- Suspended drywall ceiling framing and finishing in reception, conference rooms

- Access panels at all concealed valves, dampers, and serviceable equipment

- Coordinate ceiling grid layout with MEP for diffuser, light, and sprinkler head locations

5. SECOND FIX MEP (LIGHTS, GRILLES, SOCKETS)

- Install all light fixtures: recessed LED downlights, linear fixtures, pendants per lighting plan

- Install HVAC supply diffusers, return air grilles, and exhaust grilles

- Install electrical devices: duplex receptacles, switches, dimmers, data outlets

- Install DDC/BMS zone controllers and programmable thermostats

- Occupancy/vacancy sensors per NYC Energy Code

- Emergency and exit lighting per code

- All second fix to be complete before finish painting begins

6. FINISHES

- Drywall taping, jointing, and sanding to Level 4 finish

- Prime and first coat paint on all new drywall surfaces (low-VOC, Benjamin Moore or equal)

- Accent walls per design intent

- Floor leveling and preparation: self-leveling underlayment for flatness tolerance

- Moisture testing per ASTM F2170 prior to flooring installation

- Carpet tile installation in offices and conference rooms

- LVT/vinyl flooring installation in open areas and circulation

- Rubber or wood base installation throughout per finish schedule

- Final coat paint and touch-up after all trades complete trim work

7. GLASS PARTITIONS & MILLWORK

- Full-height glass partitions at conference rooms (1/2" tempered clear glass)

- Glass doors with patch fittings or pivot hardware

- Privacy film or frosting bands at 42" AFF where indicated

- Door frame installation: hollow metal at rated locations, wood at standard

- Solid core doors with commercial-grade lever hardware (ADA compliant)

- Fixed joinery/millwork: custom reception desk with stone or solid surface countertop

- Pantry cabinetry: upper and lower cabinets with quartz countertops and backsplash

- All millwork shop drawings submitted for approval prior to fabrication

8. FF&E & TECHNOLOGY

- Coordinate furniture delivery with building freight elevator schedule

- Workstation and loose furniture delivery to floor

- On-site furniture assembly: workstations, task chairs, conference tables, lounge seating

- Pantry appliances: refrigerator, microwave, dishwasher, coffee machine

- Server rack installation in IDF/server room: rack, UPS connection, grounding

- Data patching: terminate and test all Cat6A drops, label all ports

- Wireless access point installation per RF survey

- Conference room AV: displays, cameras, soundbars, wireless presentation

- Access control card readers at main entry and server room

9. COMMISSIONING & CLOSEOUT

- MEP testing and commissioning: HVAC airflow verification, electrical circuit testing

- Test and Balance (TAB) by AABC/NEBB certified contractor

- DDC/BMS programming verification and point-to-point checkout

- Final fire alarm testing: FDNY acceptance test, Certificate of Approval

- Final fire sprinkler inspection and DOB sign-off

- Final deep clean: all surfaces, windows, floors, restrooms

- Punch list walkthrough with A/E team and owner

- Rectification of all punch list defects by responsible trades

- Furnish O&M manuals, as-built drawings, warranty documentation

- Project handover: keys, access cards, attic stock, spare parts

10. EXCLUSIONS

- Base building HVAC system upgrades beyond tenant riser taps

- Structural modifications requiring SE review

- Exterior facade, window, or roof work

- IT equipment (servers, switches, routers, computers, phones)

- Tenant's personal property, artwork, or decorative accessories

- Moving and relocation services

- After-hours HVAC charges by building during construction

- Building management fees or landlord review fees