## Construction Schedule
CONTECH OFFICE FIT-OUT — Construction Schedule (P6 Export)
Project Start: March 30, 2026 ¦ Completion: October 13, 2026 ¦ Duration: ~28 Weeks ¦ All Activities Critical Path
ID | Activity | Duration (Days) | Start | End | Responsible | Wk 1 03/30 | Wk 2 04/06 | Wk 3 04/13 | Wk 4 04/20 | Wk 5 04/27 | Wk 6 05/04 | Wk 7 05/11 | Wk 8 05/18 | Wk 9 05/25 | Wk 10 06/01 | Wk 11 06/08 | Wk 12 06/15 | Wk 13 06/22 | Wk 14 06/29 | Wk 15 07/06 | Wk 16 07/13 | Wk 17 07/20 | Wk 18 07/27 | Wk 19 08/03 | Wk 20 08/10 | Wk 21 08/17 | Wk 22 08/24 | Wk 23 08/31 | Wk 24 09/07 | Wk 25 09/14 | Wk 26 09/21 | Wk 27 09/28 | Wk 28 10/05 | Wk 29 10/12 | Wk 30 10/19
MOBILIZATION & DEMO
A1000 | Site Mobilization | 5 | 03/30/2026 | 04/03/2026 | GC
A1010 | Demolition & Site Clearance | 2 | 04/06/2026 | 04/07/2026 | Demo Sub
FRAMING & ROUGH-IN
A1020 | Layout Marking & Wall Track Installation | 5 | 04/08/2026 | 04/14/2026 | Drywall Sub
A1030 | Metal Stud Partitioning | 10 | 04/15/2026 | 04/28/2026 | Drywall Sub
A1040 | First Fix MEP (Above Ceiling & In-Wall) | 15 | 04/29/2026 | 05/19/2026 | MEP Contractor
A1050 | Fire Sprinkler Pipe Modification | 7 | 05/20/2026 | 05/28/2026 | FP Sub
DRYWALL & CEILING
A1060 | Single Side Drywall Closing | 5 | 05/29/2026 | 06/04/2026 | Drywall Sub
A1070 | Ceiling Grid & Hangers Installation | 10 | 06/05/2026 | 06/18/2026 | Ceiling Sub
MEP SECOND FIX
A1080 | Second Fix MEP (Lights, Grilles, Sockets) | 12 | 06/19/2026 | 07/06/2026 | MEP Contractor
FINISHES
A1090 | Wall Taping, Jointing & First Coat Paint | 8 | 07/07/2026 | 07/16/2026 | Painter
A1100 | Floor Leveling & Preparation | 3 | 07/17/2026 | 07/21/2026 | Flooring Sub
A1110 | Carpet / Vinyl Flooring Installation | 7 | 07/22/2026 | 07/30/2026 | Flooring Sub
GLAZING & MILLWORK
A1120 | Glass Partition & Door Frame Installation | 10 | 07/31/2026 | 08/13/2026 | Glass Sub
A1130 | Fixed Joinery / Millwork (Reception & Pantry) | 10 | 08/14/2026 | 08/27/2026 | Millwork Sub
FF&E & TECHNOLOGY
A1140 | Workstation & Loose Furniture Delivery | 2 | 08/28/2026 | 08/31/2026 | Furniture Dealer
A1150 | On-Site Furniture Assembly | 5 | 09/01/2026 | 09/07/2026 | Furniture Dealer
A1160 | Server Rack Installation & Patching | 5 | 09/08/2026 | 09/14/2026 | LV / IT Sub
COMMISSIONING & CLOSEOUT
A1170 | MEP Testing & Commissioning (Air/Power) | 7 | 09/15/2026 | 09/23/2026 | MEP Contractor
A1180 | Final Fire Alarm / Sprinkler Inspection | 2 | 09/24/2026 | 09/25/2026 | FP Sub
A1190 | Final Deep Clean | 3 | 09/28/2026 | 09/30/2026 | Cleaning
A1200 | Punch List Walkthrough | 3 | 10/01/2026 | 10/05/2026 | A/E + Owner
A1210 | Rectification of Defects | 5 | 10/06/2026 | 10/12/2026 | All Trades
A1220 | Project Handover | 1 | 10/13/2026 | 10/13/2026 | GC
LEGEND:
MOBILIZATION & DEMO
FRAMING & ROUGH-IN
DRYWALL & CEILING
MEP SECOND FIX
FINISHES
GLAZING & MILLWORK
FF&E & TECHNOLOGY
COMMISSIONING & CLOSEOUT
SOURCE: | Primavera P6 XER Export — Contech Office Fit-out

## Milestones
# | Milestone | Target Date | Status
1 | Site Mobilization Complete | 04/03/2026 | Pending
2 | Demolition Complete | 04/07/2026 | Pending
3 | Framing Complete | 04/28/2026 | Pending
4 | First Fix MEP Complete | 05/19/2026 | Pending
5 | Drywall & Ceiling Complete | 06/18/2026 | Pending
6 | Second Fix MEP Complete | 07/06/2026 | Pending
7 | Finishes Complete | 07/30/2026 | Pending
8 | Glass & Millwork Complete | 08/27/2026 | Pending
9 | FF&E Install Complete | 09/14/2026 | Pending
10 | MEP Commissioning Complete | 09/23/2026 | Pending
11 | Final Inspections Complete | 09/25/2026 | Pending
12 | Punch List Complete | 10/12/2026 | Pending
13 | Project Handover | 10/13/2026 | Pending